## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Decide on a Project and make group on teams | 1 | 1 | 1 | 1 | 100%
What Programming language? | 2 | 1 | 2 | 1 | 100%
What Development Environment to use? | 2 | 1 | 2 | 1 | 100%
Sort out who will focus on what area? | 3 | 1 | 3 | 1 | 100%
Decide on project development environment versions | 4 | 1 | 4 | 4 | 100%
Create a Mongo Server Cluster | 5 | 1 | 5 | 1 | 100%
Find an API for the project | 5 | 2 | 5 | 2 | 100%
Create a base Project | 6 | 1 | 6 | 1 | 100%
Create a home page | 7 | 2 | 7 | 2 | 75%
Add Mongo Server to project | 8 | 1 | 8 | 1 | 100%
Add API Call | 8 | 1 | 8 | 1 | 100%
Allow user to receive data from MongoDB server | 9 | 2 | 9 | 2 | 85%
Start the dissertation | 10 | 1 | 10 | 1 | 100%
Complete the introduction and Abstract | 11 | 1 | 11 | 1 | 100%
Allow user to send data to MongoDB serve | 12 | 1 | 12 | 1 | 0%
Implement the API to output weather data | 13 | 1 | 13 | 1 | 0%
Create new pages to show user data | 13 | 2 | 13 | 2 | 0%
Create tables and reports to output saved user data | 14 | 1 | 14 | 1 | 0%
Add the created data to the new page | 15 | 1 | 15 | 1 | 0%
Create weekly/monthly reports for user Complete Methodology section | 14 | 1 | 14 | 1 | 0%
Complete System Design section | 14 | 2 | 14 | 2 | 0%
Complete Methodology section | 16 | 2 | 16 | 2 | 0%
When development is stable, add IOS implementation to app | 17 | 1 | 17 | 1 | 0%
Complete System Evaluation section | 18 | 1 | 18 | 1 | 0%
Complete final 3 sections of dissertation | 19 | 1 | 15 | 5 | 0%
Finalize App | 18 | 2 | 18 | 2 | 0%